## Defect Tracker
Sl No | Submitted Date | Description | Detected Sprint | Assigned To
1 | 2025-11-27 | OCR not correctly extracting applicant details from passport image | Sprint 1 | Backend Team
2 | 2025-11-28 | Missing values causing incorrect visa approval prediction | Sprint 2 | Backend Team
3 | 2025-12-06 | Regression model accuracy not matching validation results | Sprint 2 | ML Team
4 | 2025-12-10 | Processing time estimator showing negative values | Sprint 2 | ML Team
5 | 2025-12-12 | Visa status result not displayed on UI after prediction | Sprint 3 | Frontend Team
6 | 2025-12-17 | Invalid document upload not handled properly | Sprint 3 | Frontend Team
7 | 2025-12-26 | API response delay during peak requests | Sprint 3 | Backend Team
8 | 2026-01-02 | Dashboard charts not updating after model retraining | Sprint 4 | Frontend Team
9 | 2026-01-09 | Incorrect visa rejection reason displayed | Sprint 4 | Backend Team
10 | 2026-01-16 | UI alignment and text formatting issues | Sprint 4 | Frontend Team